## WBS
Sprint | Task | Task's outcomes | Assignee | Start Date | Deadline | End Date | Status
Sprint 1 | Collect user requirements | General procedure | Hoang Thi Hoai Thuong | 2023-05-08 | 2023-05-12 | 2023-05-09 | Done
|  | Report 3 | Hoang Thi Hoai Thuong | 2023-05-08 | 2023-05-12 | 2023-05-09 | Done
| Training |  | Everyone | 2023-05-10 | 2023-05-12 | 2023-05-10 | Done
| Write Report 1 |  | Hoang Thi Hoai Thuong | 2023-05-11 | 2023-05-12 | 2023-05-11 | Done
| Plan the project |  | Hoang Thi Hoai Thuong | 2023-05-11 | 2023-05-12 | 2023-05-12 | Done
Sprint 2 | Design database |  | Mai Hoang Duong | 2023-05-15 | 2023-05-19 | 2023-05-18 | Done
| Design UI | Figma prototype | Nguyen Dang Truong Anh | 2023-05-15 | 2023-05-19 | 2023-05-17 | Done
| Set up the project base |  | Bui The Hien Hoang Thi Hoai Thuong Mai Hoang Duong | 2023-05-17 | 2023-05-19 | 2023-05-18 | Done
| Write Report 2 |  | Hoang Thi Hoai Thuong | 2023-05-18 | 2023-05-19 | 2023-05-19 | Done
Sprint 3 | Implement API for [Create a conference] feature | Create a conference API | Hoang Thi Hoai Thuong | 2023-05-22 | 2023-05-26 | 2023-05-23 | Done
|  | Edit a conference API | Hoang Thi Hoai Thuong | 2023-05-22 | 2023-05-26 | 2023-05-23 | Done
|  | Search PC Chair API | Hoang Thi Hoai Thuong | 2023-05-22 | 2023-05-26 | 2023-05-23 | Done
|  | Add user conference API | Hoang Thi Hoai Thuong | 2023-05-22 | 2023-05-26 | 2023-05-23 | Done
| Implement UI for [Create a conference] feature | Add Logo for conference | Bui The Hien | 2023-05-23 | 2023-05-26 | 2023-05-24 | Done
|  | Create conference | Bui The Hien | 2023-05-23 | 2023-05-26 | 2023-05-24 | Done
|  | Implement add user to conference | Bui The Hien | 2023-05-23 | 2023-05-26 | 2023-05-24 | Done
| Implement API for [Set up conference website] feature | Create & Update template | Mai Hoang Duong | 2023-05-23 | 2023-05-26 | 2023-05-24 | Done
|  | Save & Update Navbar Website | Mai Hoang Duong | 2023-05-23 | 2023-05-26 | 2023-05-24 | Done
|  | Create & Update website | Mai Hoang Duong | 2023-05-23 | 2023-05-26 | 2023-05-24 | Done
| Implement UI for [Set up conference website] feature | Choose template | Bui The Hien | 2023-05-24 | 2023-05-26 | 2023-05-25 | Done
|  | Edit Web content | Bui The Hien | 2023-05-24 | 2023-05-26 | 2023-05-25 | Done
|  | Export into files html | Bui The Hien | 2023-05-24 | 2023-05-26 | 2023-05-25 | Done
| Implement API for [Configure conference's track list] feature | Create new track API | Hoang Thi Hoai Thuong | 2023-05-24 | 2023-05-26 | 2023-05-25 | Done
|  | Edit track API | Hoang Thi Hoai Thuong | 2023-05-24 | 2023-05-26 | 2023-05-25 | Done
|  | Get list tracks API | Hoang Thi Hoai Thuong | 2023-05-24 | 2023-05-26 | 2023-05-25 | Done
| Implement UI for [Configure conference's track list] feature | Create new track | Bui The Hien | 2023-05-24 | 2023-05-26 | 2023-05-25 | Done
|  | Edit track | Bui The Hien | 2023-05-24 | 2023-05-26 | 2023-05-25 | Done
| Implement API for [Configure conference's subject areas] feature | Create subject area API | Hoang Thi Hoai Thuong | 2023-05-25 | 2023-05-26 | 2023-05-26 | Done
|  | Edit subject area API | Hoang Thi Hoai Thuong | 2023-05-25 | 2023-05-26 | 2023-05-26 | Done
|  | Get list subject areas API | Hoang Thi Hoai Thuong | 2023-05-25 | 2023-05-26 | 2023-05-26 | Done
|  | Remove subject area API | Hoang Thi Hoai Thuong | 2023-05-25 | 2023-05-26 | 2023-05-26 | Done
| Implement UI for [Configure conference's subject areas] feature | Create subject area | Bui The Hien | 2023-05-25 | 2023-05-26 | 2023-05-26 | Done
|  | Edit subject area | Bui The Hien | 2023-05-25 | 2023-05-26 | 2023-05-26 | Done
|  | Display list subject areas | Bui The Hien | 2023-05-25 | 2023-05-26 | 2023-05-26 | Done
|  | Suggest subject area for user | Bui The Hien | 2023-05-25 | 2023-05-26 | 2023-05-26 | Done
|  | Remove subject area | Bui The Hien | 2023-05-25 | 2023-05-26 | 2023-05-26 | Done
Sprint 4 | Implement API for [Configure conference's submission questions] feature | Get list submission questions API | Mai Hoang Duong | 2023-05-29 | 2023-06-02 | 2023-05-30 | Done
|  | Update list submission questions API | Mai Hoang Duong | 2023-05-29 | 2023-06-02 | 2023-05-30 | Done
| Implement UI for [Configure conference's submission questions] feature | Dispaly submission question | Nguyen Dang Truong Anh | 2023-05-30 | 2023-06-02 | 2023-05-31 | Done
|  | Update submission question | Nguyen Dang Truong Anh | 2023-05-30 | 2023-06-02 | 2023-05-31 | Done
| Implement API for [Configure conference's submission settings] feature | Get submission settings API | Hoang Thi Hoai Thuong | 2023-05-30 | 2023-06-02 | 2023-05-31 | Done
|  | Update submission settings API | Hoang Thi Hoai Thuong | 2023-05-30 | 2023-06-02 | 2023-05-31 | Done
| Implement UI for [Configure conference's submission settings] feature | Dispaly submission settings | Bui The Hien | 2023-05-31 | 2023-06-02 | 2023-06-01 | Done
|  | Edit submission settings | Bui The Hien | 2023-05-31 | 2023-06-02 | 2023-06-01 | Done
| Implement API for [Configure conference's decision-making criteria] feature | Get decision criteria settings API | Hoang Thi Hoai Thuong | 2023-05-31 | 2023-06-02 | 2023-06-01 | Done
|  | Update decision criteria settings API | Hoang Thi Hoai Thuong | 2023-05-31 | 2023-06-02 | 2023-06-01 | Done
| Implement UI for [Configure conference's decision-making criteria] feature | Display checklist task settings | Bui The Hien | 2023-06-01 | 2023-06-02 | 2023-06-02 | Done
|  | Display decision criteria settings | Bui The Hien | 2023-06-01 | 2023-06-02 | 2023-06-02 | Done
|  | Update decision criteria settings | Bui The Hien | 2023-06-01 | 2023-06-02 | 2023-06-02 | Done
Sprint 5 | Implement API for [Configure conference's camera-ready settings] feature | Get camera ready settings API | Hoang Thi Hoai Thuong | 2023-06-05 | 2023-06-09 | 2023-06-05 | Done
|  | Update camera ready settings API | Hoang Thi Hoai Thuong | 2023-06-05 | 2023-06-09 | 2023-06-05 | Done
| Implement UI for [Configure conference's camera-ready settings] feature | Display cameara ready settings | Bui The Hien | 2023-06-05 | 2023-06-09 | 2023-06-07 | Done
|  | Update cameara ready settings | Bui The Hien | 2023-06-06 | 2023-06-09 | 2023-06-07 | Done
| Implement API for [Configure conference's registration settings] feature | Get registration setting API | Hoang Thi Hoai Thuong | 2023-06-06 | 2023-06-09 | 2023-06-07 | Done
|  | Update registration setting API | Hoang Thi Hoai Thuong | 2023-06-06 | 2023-06-09 | 2023-06-07 | Done
| Implement UI for [Configure conference's registration settings] feature | Display registration setting | Nguyen Dang Truong Anh | 2023-06-06 | 2023-06-09 | 2023-06-09 | Done
|  | Handle free of charge option | Bui The Hien | 2023-06-06 | 2023-06-09 | 2023-06-09 | Done
|  | Create new registration option | Nguyen Dang Truong Anh | 2023-06-08 | 2023-06-09 | 2023-06-09 | Done
|  | Edit registration option | Nguyen Dang Truong Anh | 2023-06-08 | 2023-06-09 | 2023-06-09 | Done
|  | Implement create registration setting | Nguyen Dang Truong Anh | 2023-06-08 | 2023-06-09 | 2023-06-09 | Done
| Implement API for [Configure conference's presentation settings] feature | Get Presentation settings API | Bui The Hien | 2023-06-08 | 2023-06-09 | 2023-06-09 | Done
|  | Update Presentation settings API | Bui The Hien | 2023-06-08 | 2023-06-09 | 2023-06-09 | Done
| Implement UI for [Configure conference's presentation settings] feature | Display presentation settings | Bui The Hien | 2023-06-08 | 2023-06-09 | 2023-06-09 | Done
|  | Update presentation settings | Bui The Hien | 2023-06-08 | 2023-06-09 | 2023-06-09 | Done
Sprint 6 | Implement API for [Submit papers] feature | Create paper submission API | Hoang Thi Hoai Thuong | 2023-06-12 | 2023-06-16 | 2023-06-12 | Done
|  | Search Author API | Hoang Thi Hoai Thuong | 2023-06-12 | 2023-06-16 | 2023-06-12 | Done
|  | Search Outsider by email API | Mai Hoang Duong | 2023-06-12 | 2023-06-16 | 2023-06-12 | Done
|  | Create Outsider API | Mai Hoang Duong | 2023-06-12 | 2023-06-16 | 2023-06-12 | Done
|  | Get list author submission API | Hoang Thi Hoai Thuong | 2023-06-12 | 2023-06-16 | 2023-06-13 | Done
|  | Get list submisison assigned to reviewer API | Hoang Thi Hoai Thuong | 2023-06-12 | 2023-06-16 | 2023-06-13 | Done
|  | Get list all submisison API | Hoang Thi Hoai Thuong | 2023-06-12 | 2023-06-16 | 2023-06-13 | Done
|  | Get submission statistic API | Hoang Thi Hoai Thuong | 2023-06-12 | 2023-06-16 | 2023-06-13 | Done
|  | Get list conference users API | Hoang Thi Hoai Thuong | 2023-06-12 | 2023-06-16 | 2023-06-13 | Done
|  | Get submisiosn summary API | Hoang Thi Hoai Thuong | 2023-06-12 | 2023-06-16 | 2023-06-13 | Done
|  | Get statistic for conference user API | Hoang Thi Hoai Thuong | 2023-06-12 | 2023-06-16 | 2023-06-13 | Done
| Implement UI for [Submit papers] feature | Display submisiosn summary API | Nguyen Dang Truong Anh | 2023-06-13 | 2023-06-16 | 2023-06-14 | Done
|  | Display author submisison | Nguyen Dang Truong Anh | 2023-06-13 | 2023-06-16 | 2023-06-14 | Done
|  | Display reviewer assigned submission | Nguyen Dang Truong Anh | 2023-06-13 | 2023-06-16 | 2023-06-14 | Done
|  | Display all submisison in conference | Nguyen Dang Truong Anh | 2023-06-13 | 2023-06-16 | 2023-06-14 | Done
|  | Implement statistic for submisison | Nguyen Dang Truong Anh | 2023-06-13 | 2023-06-16 | 2023-06-14 | Done
|  | Implement statistic for conference user | Nguyen Dang Truong Anh | 2023-06-13 | 2023-06-16 | 2023-06-14 | Done
|  | View submisison summary | Nguyen Dang Truong Anh | 2023-06-13 | 2023-06-16 | 2023-06-14 | Done
|  | Create paper submission | Nguyen Dang Truong Anh | 2023-06-13 | 2023-06-16 | 2023-06-14 | Done
| Implement API for [Declare conflicts of interest] feature | Get submission brief info API | Hoang Thi Hoai Thuong | 2023-06-14 | 2023-06-16 | 2023-06-16 | Done
|  | Get list reviewers conflict API | Hoang Thi Hoai Thuong | 2023-06-14 | 2023-06-16 | 2023-06-16 | Done
|  | Get list conflicts API | Hoang Thi Hoai Thuong | 2023-06-14 | 2023-06-16 | 2023-06-16 | Done
| Implement UI for [Declare conflicts of interest] feature | Save conflict with reviewers API | Nguyen Dang Truong Anh | 2023-06-14 | 2023-06-16 | 2023-06-16 | Done
|  | Display table reviewers with conflicts | Nguyen Dang Truong Anh | 2023-06-14 | 2023-06-16 | 2023-06-16 | Done
|  | Implement list of conflicts | Nguyen Dang Truong Anh | 2023-06-14 | 2023-06-16 | 2023-06-16 | Done
|  | Handle select conflict for each reviewer | Nguyen Dang Truong Anh | 2023-06-14 | 2023-06-16 | 2023-06-16 | Done
Sprint 7 | Implement API for [Assign reviewers] feature | Implement save conflict with reviewers for submisison | Mai Hoang Duong | 2023-06-19 | 2023-06-23 | 2023-06-19 | Done
|  | Get list reviewers API | Mai Hoang Duong | 2023-06-19 | 2023-06-23 | 2023-06-19 | Done
| Implement UI for [Assign reviewers] feature | Assign reviewers for submisison API | Nguyen Dang Truong Anh | 2023-06-19 | 2023-06-23 | 2023-06-19 | Done
|  | Display table of reviewers for assign | Nguyen Dang Truong Anh | 2023-06-19 | 2023-06-23 | 2023-06-19 | Done
|  | Handle color highlight for 2 top most reviewer relevance score | Nguyen Dang Truong Anh | 2023-06-19 | 2023-06-23 | 2023-06-21 | Done
|  | Implement assigned reviewers | Nguyen Dang Truong Anh | 2023-06-20 | 2023-06-23 | 2023-06-21 | Done
| Implement API for [Review] feature | Tab to display assigned reviewers | Hoang Thi Hoai Thuong | 2023-06-20 | 2023-06-23 | 2023-06-21 | Done
|  | Get list reviews submisison role PC Chair API | Hoang Thi Hoai Thuong | 2023-06-20 | 2023-06-23 | 2023-06-21 | Done
|  | Get list reviews submission role Author API | Hoang Thi Hoai Thuong | 2023-06-20 | 2023-06-23 | 2023-06-21 | Done
|  | Get review API | Hoang Thi Hoai Thuong | 2023-06-20 | 2023-06-23 | 2023-06-21 | Done
|  | Submit review submisison API | Hoang Thi Hoai Thuong | 2023-06-21 | 2023-06-23 | 2023-06-22 | Done
|  | Edit review API | Mai Hoang Duong | 2023-06-21 | 2023-06-23 | 2023-06-22 | Done
|  | Get list reviewers in conference API | Mai Hoang Duong | 2023-06-21 | 2023-06-23 | 2023-06-22 | Done
|  | Get reviewer statistic API | Hoang Thi Hoai Thuong | 2023-06-21 | 2023-06-23 | 2023-06-22 | Done
|  | Get reviewer review info API | Hoang Thi Hoai Thuong | 2023-06-21 | 2023-06-23 | 2023-06-22 | Done
|  | Edit reviewer quota API | Hoang Thi Hoai Thuong | 2023-06-21 | 2023-06-23 | 2023-06-22 | Done
|  | Get list subject area API | Hoang Thi Hoai Thuong | 2023-06-22 | 2023-06-23 | 2023-06-23 | Done
| Implement UI for [Review] feature | Submit reviewer subject area API | Nguyen Dang Truong Anh | 2023-06-22 | 2023-06-23 | 2023-06-23 | Done
|  | PC Chair view review of submission | Nguyen Dang Truong Anh | 2023-06-22 | 2023-06-23 | 2023-06-23 | Done
|  | Author view review of submisson | Nguyen Dang Truong Anh | 2023-06-22 | 2023-06-23 | 2023-06-23 | Done
|  | Reviewer view review of submisison | Nguyen Dang Truong Anh | 2023-06-22 | 2023-06-23 | 2023-06-23 | Done
|  | Reviewer edit review | Nguyen Dang Truong Anh | 2023-06-22 | 2023-06-23 | 2023-06-23 | Done
|  | Reviewer submit review | Nguyen Dang Truong Anh | 2023-06-22 | 2023-06-23 | 2023-06-23 | Done
|  | PC Chair view list reviewers in conference | Nguyen Dang Truong Anh | 2023-06-22 | 2023-06-23 | 2023-06-23 | Done
|  | PC Chair view reviews of reviewers | Nguyen Dang Truong Anh | 2023-06-23 | 2023-06-23 | 2023-06-23 | Done
|  | Implement reviewer statistic | Nguyen Dang Truong Anh | 2023-06-23 | 2023-06-23 | 2023-06-23 | Done
|  | Submit reviewer quota | Nguyen Dang Truong Anh | 2023-06-23 | 2023-06-23 | 2023-06-23 | Done
Sprint 8 | Implement API for [Decide on papers] feature | Implement reviewer select subject area | Bui The Hien | 2023-06-26 | 2023-06-30 | 2023-06-26 | Done
|  | Get list paper status API | Bui The Hien | 2023-06-26 | 2023-06-30 | 2023-06-26 | Done
|  | Submit Decision API | Bui The Hien | 2023-06-26 | 2023-06-30 | 2023-06-26 | Done
|  | Get list decision criteria API | Mai Hoang Duong | 2023-06-26 | 2023-06-30 | 2023-06-26 | Done
| Implement UI for [Decide on papers] feature | Submit Chair note API | Nguyen Dang Truong Anh | 2023-06-26 | 2023-06-30 | 2023-06-27 | Done
|  | Implement decide on paper | Bui The Hien | 2023-06-26 | 2023-06-30 | 2023-06-27 | Done
|  | Submit Chair note | Nguyen Dang Truong Anh | 2023-06-27 | 2023-06-30 | 2023-06-27 | Done
|  | Get list status | Bui The Hien | 2023-06-27 | 2023-06-30 | 2023-06-27 | Done
| Implement API for [Notify result to authors] feature | Display decision criteria | Mai Hoang Duong | 2023-06-27 | 2023-06-30 | 2023-06-27 | Done
|  | Create email template API | Mai Hoang Duong | 2023-06-27 | 2023-06-30 | 2023-06-28 | Done
|  | Edit email template API | Mai Hoang Duong | 2023-06-27 | 2023-06-30 | 2023-06-28 | Done
|  | Get list placeholder API | Mai Hoang Duong | 2023-06-27 | 2023-06-30 | 2023-06-28 | Done
| Implement UI for [Notify result to authors] feature | Send email API | Bui The Hien | 2023-06-27 | 2023-06-30 | 2023-06-28 | Done
|  | Implement create email template | Bui The Hien | 2023-06-28 | 2023-06-30 | 2023-06-29 | Done
|  | Implment edit email template | Nguyen Dang Truong Anh | 2023-06-28 | 2023-06-30 | 2023-06-29 | Done
|  | Preview email send | Nguyen Dang Truong Anh | 2023-06-28 | 2023-06-30 | 2023-06-29 | Done
| Write Report 3 |  | Hoang Thi Hoai Thuong | 2023-06-29 | 2023-06-30 | 2023-06-30 | Done
Sprint 9 | Implement API for [Preliminary access] feature | Implement placeholder list | Hoang Thi Hoai Thuong | 2023-07-10 | 2023-07-14 | 2023-07-11 | Done
|  | Get submisison information API | Hoang Thi Hoai Thuong | 2023-07-11 | 2023-07-14 | 2023-07-12 | Done
|  | Submit desk reject API | Hoang Thi Hoai Thuong | 2023-07-11 | 2023-07-14 | 2023-07-12 | Done
| Implement UI for [Preliminary access] feature | Submit chair note API | Nguyen Dang Truong Anh | 2023-07-12 | 2023-07-14 | 2023-07-13 | Done
|  | Display submission information | Nguyen Dang Truong Anh | 2023-07-13 | 2023-07-14 | 2023-07-14 | Done
|  | Note reason why submission have desk rejection | Nguyen Dang Truong Anh | 2023-07-13 | 2023-07-14 | 2023-07-14 | Done
Sprint 10 | Implement API for [Revision] feature | Desk reject a submission | Hoang Thi Hoai Thuong | 2023-07-17 | 2023-07-21 | 2023-07-18 | Done
|  | Submit revision API | Hoang Thi Hoai Thuong | 2023-07-17 | 2023-07-21 | 2023-07-18 | Done
| Implement UI for [Revision] feature | Edit revision API | Bui The Hien | 2023-07-17 | 2023-07-21 | 2023-07-19 | Done
|  | Display submission information | Bui The Hien | 2023-07-17 | 2023-07-21 | 2023-07-19 | Done
Sprint 11 | Implement API for [Request for camera-ready submission] feature | Submit revision files | Hoang Thi Hoai Thuong | 2023-07-24 | 2023-07-28 | 2023-07-24 | Done
| Implement UI for [Request for camera-ready submission] feature | Request camera ready API | Bui The Hien | 2023-07-24 | 2023-07-28 | 2023-07-24 | Done
| Implement API for [Submit camera-ready] feature | Display submission for authors to submit camera ready | Hoang Thi Hoai Thuong | 2023-07-24 | 2023-07-28 | 2023-07-24 | Done
|  | Create camera ready API | Hoang Thi Hoai Thuong | 2023-07-24 | 2023-07-28 | 2023-07-24 | Done
|  | Edit camera ready API | Mai Hoang Duong | 2023-07-24 | 2023-07-28 | 2023-07-24 | Done
|  | Get manuscript API | Mai Hoang Duong | 2023-07-24 | 2023-07-28 | 2023-07-25 | Done
| Implement UI for [Submit camera-ready] feature | Download & Upload camera ready file API | Bui The Hien | 2023-07-24 | 2023-07-28 | 2023-07-25 | Done
|  | Display submission information | Bui The Hien | 2023-07-24 | 2023-07-28 | 2023-07-25 | Done
|  | Submit camera ready files | Bui The Hien | 2023-07-24 | 2023-07-28 | 2023-07-25 | Done
| Implement API for [Register papers] feature | Submit copyright files | Hoang Thi Hoai Thuong | 2023-07-24 | 2023-07-28 | 2023-07-25 | Done
|  | Get registration order API | Hoang Thi Hoai Thuong | 2023-07-24 | 2023-07-28 | 2023-07-26 | Done
|  | Create order API | Hoang Thi Hoai Thuong | 2023-07-24 | 2023-07-28 | 2023-07-26 | Done
| Implement UI for [Register papers] feature | Get list registration manuscript API | Bui The Hien | 2023-07-24 | 2023-07-28 | 2023-07-26 | Done
|  | Display options to choose for payment | Bui The Hien | 2023-07-24 | 2023-07-28 | 2023-07-26 | Done
|  | Display registrable submissions | Bui The Hien | 2023-07-24 | 2023-07-28 | 2023-07-27 | Done
|  | Make payment with selected submissions | Nguyen Dang Truong Anh | 2023-07-24 | 2023-07-28 | 2023-07-27 | Done
|  | Payment | Nguyen Dang Truong Anh | 2023-07-24 | 2023-07-28 | 2023-07-27 | Done
Sprint 12 | Implement API for [Request for presentation submission] feature | Implement author manuscript | Bui The Hien | 2023-07-31 | 2023-08-04 | 2023-08-01 | Done
|  | Bulk request presentation API | Bui The Hien | 2023-07-31 | 2023-08-04 | 2023-08-01 | Done
| Implement UI for [Request for presentation submission] feature | Download Presentation API | Nguyen Dang Truong Anh | 2023-07-31 | 2023-08-04 | 2023-08-01 | Done
| Implement API for [Submit presentation] feature | Display submission for authors to submit presetations | Bui The Hien | 2023-07-31 | 2023-08-04 | 2023-08-02 | Done
|  | Submit Presentation API | Bui The Hien | 2023-07-31 | 2023-08-04 | 2023-08-02 | Done
| Implement UI for [Submit presentation] feature | Get presentation submisison API | Bui The Hien | 2023-07-31 | 2023-08-04 | 2023-08-03 | Done
|  | Display tasks list | Bui The Hien | 2023-07-31 | 2023-08-04 | 2023-08-03 | Done
|  | Display authors list | Bui The Hien | 2023-07-31 | 2023-08-04 | 2023-08-03 | Done
Sprint 13 | Implement API for [Produce statistical summaries and reports of a conference] feature | Submit presenttion files and presenters. | Hoang Thi Hoai Thuong | 2023-08-07 | 2023-08-11 | 2023-08-08 | Done
| Implement UI for [Produce statistical summaries and reports of a conference] feature | Produce statistical summaries and report API | Bui The Hien | 2023-08-07 | 2023-08-11 | 2023-08-08 | Done
| Write report 4 |  | Mai Hoang Duong | 2023-08-07 | 2023-08-11 | 2023-08-09 | Done
Sprint 14 | Implement API for [Research profile feature] feature | Delete Educations, Employments, Sholarships, Awards, Skills, Reseaches, Publications API | Mai Hoang Duong | 2023-08-14 | 2023-08-18 | 2023-08-15 | Done
|  | Create Overview, Educations, Employments, Sholarships, Awards, Skills, Reseaches, Publications API | Mai Hoang Duong | 2023-08-14 | 2023-08-18 | 2023-08-15 | Done
|  | Update Overview, Educations, Employments, Sholarships, Awards, Skills, Reseaches, Publications API | Mai Hoang Duong | 2023-08-14 | 2023-08-18 | 2023-08-16 | Done
|  | Get Overview, Educations, Employments, Sholarships, Awards, Skills, Reseaches, Publications API | Mai Hoang Duong | 2023-08-14 | 2023-08-18 | 2023-08-16 | Done
| Implement UI for [Research profile feature] feature | Delete Educations, Employments, Sholarships, Awards, Skills, Reseaches, Publications | Bui The Hien | 2023-08-14 | 2023-08-18 | 2023-08-15 | Done
|  | Create Overview, Educations, Employments, Sholarships, Awards, Skills, Reseaches, Publications | Bui The Hien | 2023-08-14 | 2023-08-18 | 2023-08-15 | Done
|  | Update Overview, Educations, Employments, Sholarships, Awards, Skills, Reseaches, Publications | Bui The Hien | 2023-08-14 | 2023-08-18 | 2023-08-16 | Done
|  | Display Overview, Educations, Employments, Sholarships, Awards, Skills, Reseaches, Publications | Bui The Hien | 2023-08-14 | 2023-08-18 | 2023-08-16 | Done
Sprint 15 | - Implement integration test |  | Bui The Hien Hoang Thi Hoai Thuong Mai Hoang Duong Nguyen Dang Truong Anh | 2023-08-21 | 2023-08-25 | 2023-08-22 | Done
| - Meet the customer to demo full project’s core flow |  | Bui The Hien Hoang Thi Hoai Thuong Mai Hoang Duong Nguyen Dang Truong Anh | 2023-08-21 | 2023-08-25 | 2023-08-24 | Done
Sprint 16 | - Implement system test |  | Bui The Hien Hoang Thi Hoai Thuong Mai Hoang Duong Nguyen Dang Truong Anh | 2023-08-28 | 2023-09-01 | 2023-08-29 | Done
| - Write Report 5 |  | Nguyen Dang Truong Anh | 2023-08-28 | 2023-09-01 | 2023-09-30 | Done
Sprint 17 | - Release |  | Bui The Hien Hoang Thi Hoai Thuong Mai Hoang Duong Nguyen Dang Truong Anh | 2023-09-04 | 2023-09-08 | 2023-09-06 | Done
| - Write Report 6 |  | Bui The Hien | 2023-09-04 | 2023-09-08 | 2023-09-07 | Done
Sprint 18 | - Review all features related to projects |  | Bui The Hien Hoang Thi Hoai Thuong Mai Hoang Duong Nguyen Dang Truong Anh | 2023-09-11 | 2023-09-15 | 2023-09-12 | Done
| - Write Report 7 |  | Bui The Hien Hoang Thi Hoai Thuong Mai Hoang Duong Nguyen Dang Truong Anh | 2023-09-11 | 2023-09-15 | 2023-09-13 | Done
Sprint 19 | - Prepare for final presentation |  | Bui The Hien Hoang Thi Hoai Thuong Mai Hoang Duong Nguyen Dang Truong Anh | 2023-09-18 | 2023-09-22 | 2023-09-20 | Done